ASSIGNMENT # 2

Given a list of project activities with their time estimates and dependencies,

- Draw the project network diagram.

- Identify the critical path.

- Calculate expected project duration using PERT.

- Find slack/float for each activity.

Example Dataset:

| Activity | Predecessor | Optimistic (a) | Most Likely (m) | Pessimistic (b) |
| --- | --- | --- | --- | --- |
| A | — | 2 | 4 | 6 |
| B | A | 1 | 3 | 5 |
| C | A | 2 | 5 | 8 |
| D | B, C | 3 | 4 | 11 |