ASSIGNMENT # 2

Given a list of project activities with their time estimates and dependencies,

- Draw the project network diagram.

- Identify the critical path.

- Calculate expected project duration using PERT.

- Find slack/float for each activity.

Example Dataset:

| Activity | Predecessor | Optimistic (a) | Most Likely (m) | Pessimistic (b) |
| --- | --- | --- | --- | --- |
| A | — | 2 | 4 | 6 |
| B | A | 1 | 3 | 5 |
| C | A | 2 | 5 | 8 |
| D | B, C | 3 | 4 | 11 |

Answer:

| Activity | a | m | b | Expected Time (te) = (a + 4m + b)/6 |
| --- | --- | --- | --- | --- |
| A | 2 | 4 | 6 | (2 + 16 + 6)/6 = 4 days |
| B | 1 | 3 | 5 | (1 + 12 + 5)/6 = 3 days |
| C | 2 | 5 | 8 | (2 + 20 + 8)/6 = 5 days |
| D | 3 | 4 | 11 | (3 + 16 + 11)/6 = 5 days |

Expected durations:
A = 4, B = 3, C = 5, D = 5

2: Draw the Network Diagram: Sequence (dependencies):

A → B → D

A → C → D

B

D

Start

A

AAAAAAA

C

- Activity A starts first.

- After A finishes, both B and C can start simultaneously.

- D can only start once both B and C are finished.

3: Determine Paths and Durations

| Path | Activities | Total Duration (sum of te) |
| --- | --- | --- |
| 1 | A → B → D | 4 + 3 + 5 = 12 days |
| 2 | A → C → D | 4 + 5 + 5 = 14 days |

Critical Path:
A → C → D (because it has the longest duration)

Expected Project Duration:
14 days

4: Calculate Slack (Float) for Each Activity

Slack = Latest Start – Earliest Start

Activities on the critical path have zero slack.

Let’s find earliest and latest times (simplified):

| Activity | Duration | Earliest Start (ES) | Earliest Finish (EF) | Latest Start (LS) | Latest Finish (LF) | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 4 | 0 | 4 | 0 | 4 | 0 |
| B | 3 | 4 | 7 | 6 | 9 | 2 |
| C | 5 | 4 | 9 | 4 | 9 | 0 |
| D | 5 | 9 | 14 | 9 | 14 | 0 |

Slack Summary:

- A, C, D → 0 slack (critical path)

- B → 2 days slack

1. Forward Pass (to find ES and EF)

Used to determine the earliest times activities can start and finish.

EF= ES + Duration

ES (for first activity = 0

ES ( for other activities = max (EF of all predecessors)